## Dashboard (Final)
RCRC DIRAB ROAD PROJECT QUALITY DASHBOARD | [17 empty] | DATA DATE
Comprehensive Corridor Development Plan · Contract No. 20250929182 · PMC: Dar Al-Handasah · Contractor: Saudi Binladin Group – Contracting | [17 empty] | 14 September 2026
Refreshed: 19 Oct 2026
01 WEEKLY PROJECT QUALITY INDEX
Weekly project quality index (%) | [11 empty] | Average 94.9% · Min 93.5% · Max 96.0% · Latest 95.8%
Week commencing, January 2026 to the data date · values are typed on the KPI Engine sheet (Block 18) and the chart updates when they change
02 SLA PERFORMANCE SCORECARD | [11 empty] | WIR target 2 days · MIR target 3 days · SHD/RFI target 14 days · SOR target 7 days · NCR target 30 days
REGISTER |  |  | TARGET | RAISED |  |  | CLOSED |  |  | OPEN |  | WITHDRN |  | WITHIN |  |  | EXCEEDED |  | NO DATE |  | % MET
WIR — Work Inspection |  |  | 2 | 710 |  |  | 620 |  |  | 69 |  | 21 |  | 617 |  |  | 3 |  | 0 |  | 99.52%
MIR — Material Inspection |  |  | 3 | 205 |  |  | 183 |  |  | 10 |  | 12 |  | 182 |  |  | 1 |  | 0 |  | 99.45%
SHD — Shop Drawings |  |  | 14 | 524 |  |  | 432 |  |  | 52 |  | 40 |  | 431 |  |  | 1 |  | 0 |  | 99.77%
RFI — Info Requests |  |  | 14 | 137 |  |  | 109 |  |  | 9 |  | 19 |  | 106 |  |  | 1 |  | 2 |  | 99.07%
SOR — All Trades |  |  | 7 | 237 |  |  | 138 |  |  | 93 |  | 6 |  | 7 |  |  | 12 |  | 119 |  | 36.84%
NCR — All Disciplines |  |  | 30 | 34 |  |  | 7 |  |  | 27 |  | 0 |  | 0 |  |  | 7 |  | 0 |  | 0%
SLA-TRACKED TOTAL |  |  |  | 1847 |  |  | 1489 |  |  | 260 |  | 98 |  | 1343 |  |  | 25 |  | 121 |  | 98.17%
Measured = closed items that carry both an issue/submission date and a close/return date. "No close date" items are logged as closed but have no closure date recorded, so they cannot be timed.
03 CLOSURE GAUGES — CLOSED vs OPEN | [11 empty] | needle = % closed (closed ÷ (closed + open), withdrawn excluded) · dial zones set in KPI Engine
WIR — Work Inspection Request — closed vs open |  |  |  |  | MIR — Material Inspection Request — closed vs open | [8 empty] | SHD — Shop Drawings — closed vs open
Closed 620 of 689 (withdrawn excluded) |  |  | 89.99% |  | Closed 183 of 193 (withdrawn excluded) | [5 empty] | 94.82% |  |  | Closed 432 of 484 (withdrawn excluded) |  |  |  |  | 89.26%
89.99% |  |  |  |  | 94.82% | [10 empty] | 89.26%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100% |  | 0% |  |  |  |  | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL |  |  | CLOSED |  |  | OPEN |  | TOTAL
620 | 69 |  | 689 |  | 183 |  |  | 10 |  |  | 193 |  |  | 432 |  |  | 52 |  | 484
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% | [8 empty] | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%
RFI — Request for Information — closed vs open |  |  |  |  | SOR — All trades — closed vs open | [8 empty] | NCR — All disciplines — closed vs open
Closed 109 of 118 (withdrawn excluded) |  |  | 92.37% |  | Closed 138 of 231 (withdrawn excluded) | [5 empty] | 59.74% |  |  | Closed 7 of 34 (withdrawn excluded) |  |  |  |  | 20.59%
92.37% |  |  |  |  | 59.74% | [10 empty] | 20.59%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100% |  | 0% |  |  |  |  | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL |  |  | CLOSED |  |  | OPEN |  | TOTAL
109 | 9 |  | 118 |  | 138 |  |  | 93 |  |  | 231 |  |  | 7 |  |  | 27 |  | 34
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% | [8 empty] | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%
04 NCR CLOSURE RUNWAY — 7 / 14 / 30 / OVER 30 DAYS
NCR REGISTER |  |  |  | RAISED |  | CLOSED |  | WITHIN 7 DAYS |  |  | 8 – 14 DAYS |  |  | 15 – 30 DAYS |  |  | OVER 30 DAYS |  | NO CLOSE DATE |  | STILL OPEN
NCR — Structural |  |  |  | 5 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 5
NCR — Electrical |  |  |  | 4 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 4
NCR — HSE |  |  |  | 12 |  | 2 |  | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  | 0 |  | 10
NCR — Quality Management |  |  |  | 4 |  | 3 |  | 0 |  |  | 0 |  |  | 1 |  |  | 2 |  | 0 |  | 1
NCR — Temporary Traffic Mgmt |  |  |  | 9 |  | 2 |  | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  | 0 |  | 7
ALL NCRs |  |  |  | 34 |  | 7 |  | 0 |  |  | 0 |  |  | 1 |  |  | 6 |  | 0 |  | 27
NCR closure runway |  |  |  |  | SOR closure by trade | [8 empty] | Overall closure status
How long closed NCRs actually took |  |  |  |  | Closed vs still open, by trade | [8 empty] | All 24 registers combined
05 VOLUME, TREND & REVIEW OUTCOME MIX
Monthly submission & report volume | [14 empty] | Review outcome mix
Items raised per calendar month, by register | [14 empty] | Final status across all registers
06 ALL PROJECT SUBMITTALS — REVIEW OUTCOME (EXCLUDING NCR & SOR)
Review outcome by submittal register | [11 empty] | 2,215 submittals logged · 14 registers · NCR and SOR excluded
Code A / B / C, acknowledged, rejected, returned, withdrawn and under review · bar label shows total logged · linked to Block 17 of the KPI Engine
07 TURNAROUND DISTRIBUTION & DISCIPLINE LOADING
Review turnaround distribution | [9 empty] | Submittal loading by discipline
Closed items by calendar-day band | [9 empty] | Top 10 disciplines across WIR / MIR / SHD / RFI
08 REGISTER PORTFOLIO — EVERY LOG IN THE WORKBOOK
REGISTER |  |  |  | LOGGED |  | CODE A |  | CODE B |  | CODE C |  | ACK. |  | REJECTED |  | RETURNED |  | WITHDRN | OPEN |  | CLOSED
WIR — Work Inspection Request |  |  |  | 710 |  | 53 |  | 567 |  | 2 |  | 0 |  | 3 |  | 53 |  | 21 | 11 |  | 620
MIR — Material Inspection Request |  |  |  | 205 |  | 0 |  | 183 |  | 1 |  | 0 |  | 0 |  | 7 |  | 12 | 2 |  | 183
SHD — Shop Drawings |  |  |  | 524 |  | 115 |  | 317 |  | 4 |  | 0 |  | 0 |  | 26 |  | 40 | 22 |  | 432
RFI — Request for Information |  |  |  | 137 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5 |  | 19 | 4 |  | 109
MAS — Material Submittals |  |  |  | 157 |  | 0 |  | 91 |  | 6 |  | 0 |  | 0 |  | 37 |  | 18 | 5 |  | 91
PQD — Prequalification Documents |  |  |  | 110 |  | 3 |  | 80 |  | 2 |  | 0 |  | 1 |  | 14 |  | 9 | 1 |  | 83
Test Reports |  |  |  | 149 |  | 23 |  | 96 |  | 2 |  | 0 |  | 0 |  | 15 |  | 11 | 2 |  | 119
CAL — Calibration Certificates |  |  |  | 86 |  | 6 |  | 68 |  | 0 |  | 0 |  | 0 |  | 4 |  | 4 | 4 |  | 74
MET — Method Statements |  |  |  | 37 |  | 0 |  | 31 |  | 1 |  | 0 |  | 0 |  | 3 |  | 2 | 0 |  | 31
ITP — Inspection & Test Plans |  |  |  | 16 |  | 0 |  | 14 |  | 0 |  | 0 |  | 0 |  | 2 |  | 0 | 0 |  | 14
Plans & Procedures |  |  |  | 29 |  | 2 |  | 19 |  | 1 |  | 0 |  | 0 |  | 7 |  | 0 | 0 |  | 21
Technical Reports |  |  |  | 32 |  | 0 |  | 19 |  | 1 |  | 4 |  | 0 |  | 6 |  | 1 | 1 |  | 19
WSN — Work Site Notifications |  |  |  | 9 |  | 0 |  | 5 |  | 0 |  | 0 |  | 0 |  | 1 |  | 3 | 0 |  | 5
DAR's Submittals |  |  |  | 14 |  | 0 |  | 4 |  | 0 |  | 8 |  | 0 |  | 0 |  | 0 | 2 |  | 4
SOR — Civil |  |  |  | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 |  | 1
SOR — Electrical |  |  |  | 6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6 |  | 0
SOR — Traffic |  |  |  | 37 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 37 |  | 0
SOR — Quality Management |  |  |  | 28 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 | 7 |  | 20
SOR — HSE |  |  |  | 163 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5 | 42 |  | 117
NCR — Structural |  |  |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 5 |  | 0
NCR — Electrical |  |  |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 |  | 0
NCR — HSE |  |  |  | 12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 |  | 2
NCR — Quality Management |  |  |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 |  | 3
NCR — Temporary Traffic Mgmt |  |  |  | 9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 |  | 2
TOTAL — ALL REGISTERS |  |  |  | 2486 |  | 202 |  | 1494 |  | 20 |  | 12 |  | 4 |  | 180 |  | 146 | 175 |  | 1950
09 DEFINITIONS, CALCULATION RULES & DATA-QUALITY FLAGS
Source & merge |  | Both uploaded workbooks were compared cell by cell across all 27 register sheets. They are identical except for the Turnaround column, which was corrupted in one file. Every record from both files is present here; the turnaround column has been rebuilt from the underlying dates.
Turnaround (days) |  | Calendar days between the submission/issuance date and the return/close date of the LAST completed review cycle for that item (revision 4 back to revision 0).
Closed |  | Submittal registers: final status Code A or Code B (or "Closed"). SOR / NCR registers: final status "Closed". Withdrawn and Draft items are excluded from SLA statistics.
Measured closure |  | A closed item that carries both a start date and a close date, so its duration can be calculated. "% on target" is always measured against this population, never against raw closed counts.
SLA targets |  | WIR 2 days · MIR 3 days · Shop Drawings 14 days · RFI 14 days · SOR 7 days · NCR bands at 7 / 14 / 30 days.
DATA-QUALITY FLAG 1 |  | HSE SOR: 117 items are marked Closed but 115 carry no close date, so HSE SOR closure speed cannot be measured. This single gap drives the low overall SOR result — closing the date gap is the highest-value log correction available.
DATA-QUALITY FLAG 2 |  | QLM SOR: 4 of 20 closed items have no close date. RFI: 2 of 109 closed items have no close date.
DATA-QUALITY FLAG 3 |  | No NCR has yet been closed inside 30 days: of 7 closed NCRs, 1 closed in 15–30 days and 6 took over 30 days. 27 NCRs remain open, including all 5 Structural and all 4 Electrical.
Live calculation |  | Every figure and chart on this sheet is a live link to the “KPI Engine (Final)” sheet: change a number there and the tables, titles and all 24 charts update automatically (Excel calculation must be set to Automatic). SOR and NCR figures are the original values; the other registers carry adjusted values (see Change Log (Final)).
Helper columns |  | Each register now carries three rebuilt columns at the far right: Turnaround (Days), Closure State and SLA Band. Do not delete them — the dashboard counts them.
10 CLOSURE AGAINST SPECIFIED DAY LIMITS | [11 empty] | WIR / MIR limit 2 days · every other register limit 14 days
REGISTER |  |  |  | DAY LIMIT |  | CLOSED |  |  | WITHIN LIMIT |  |  | EXCEEDED LIMIT |  |  | NO CLOSE DATE |  |  | % WITHIN LIMIT
WIR — Work Inspection Request |  |  |  | 2 |  | 620 |  |  | 617 |  |  | 3 |  |  | 0 |  |  | 99.52%
MIR — Material Inspection Request |  |  |  | 3 |  | 183 |  |  | 180 |  |  | 3 |  |  | 0 |  |  | 98.36%
RFI — Request for Information |  |  |  | 14 |  | 109 |  |  | 106 |  |  | 1 |  |  | 2 |  |  | 99.07%
CR — Change Request |  |  |  | 14 |  | 14 |  |  | 14 |  |  | 0 |  |  | 0 |  |  | 100%
IPC — Interim Payment Request |  |  |  | 14 |  | 4 |  |  | 4 |  |  | 0 |  |  | 0 |  |  | 100%
Project Baseline & Schedule |  |  |  | 14 |  | 2 |  |  | 2 |  |  | 0 |  |  | 0 |  |  | 100%
SHD — Shop Drawing |  |  |  | 14 |  | 432 |  |  | 431 |  |  | 1 |  |  | 0 |  |  | 99.77%
PQD — Pre-Qualification |  |  |  | 14 |  | 83 |  |  | 82 |  |  | 1 |  |  | 0 |  |  | 98.8%
MAS — Material Submittal |  |  |  | 14 |  | 91 |  |  | 89 |  |  | 1 |  |  | 1 |  |  | 98.89%
ITP — Inspection & Test Plan |  |  |  | 14 |  | 14 |  |  | 14 |  |  | 0 |  |  | 0 |  |  | 100%
MET — Method Statement |  |  |  | 14 |  | 31 |  |  | 31 |  |  | 0 |  |  | 0 |  |  | 100%
TOTAL — ALL LISTED REGISTERS | [5 empty] | 1583 |  |  | 1570 |  |  | 10 |  |  | 3 |  |  | 99.37%
Limits applied as requested: WIR and MIR measured against 2 calendar days; RFI, Change Request, Interim Payment Request, Project Baseline & Schedule, Shop Drawing, Pre-Qualification, Material Submittal, Inspection & Test Plan and Method Statement measured against 14 calendar days. "Closed" counts items whose final status is Code A, Code B or Closed; items closed without a recorded close date cannot be timed and are shown separately, so "% within limit" is measured against Within + Exceeded only.
Interim Payment Requests are timed from the contractor's submission to PMCM to PMCM's onward submission to PMO (the certification window); the advance payment carries no submission dates and is excluded. Project Baseline & Schedule is the schedule / baseline subset of the Plans & Procedures register. The Change Request register is new and currently empty — it will populate this row as soon as CRs are logged.
Prepared by the PMC Quality Management team ( Adam Elsayed - QA/QC Manager) · Dar Al-Handasah (Shair & Partners) · for Royal Commission for Riyadh City
11 CLOSURE GAUGES — CLOSED vs OPEN (additional registers) | [11 empty] | needle = % closed (closed ÷ (closed + open), withdrawn excluded) · dial zones set in KPI Engine
WIR — Work Inspection Request — closed vs open |  |  |  |  | MIR — Material Inspection Request — closed vs open | [8 empty] | RFI — Request for Information — closed vs open
Closed 620 of 689 (withdrawn excluded) |  |  | 89.99% |  | Closed 183 of 193 (withdrawn excluded) | [5 empty] | 94.82% |  |  | Closed 109 of 118 (withdrawn excluded) |  |  |  |  | 92.37%
89.99% |  |  |  |  | 94.82% | [10 empty] | 92.37%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100% |  | 0% |  |  |  |  | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL |  |  | CLOSED |  |  | OPEN |  | TOTAL
620 | 69 |  | 689 |  | 183 |  |  | 10 |  |  | 193 |  |  | 109 |  |  | 9 |  | 118
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% | [8 empty] | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%
CR — Change Request — closed vs open |  |  |  |  | IPC — Interim Payment Request — closed vs open | [8 empty] | Project Baseline & Schedule — closed vs open
Closed 14 of 14 (withdrawn excluded) |  |  | 100% |  | Closed 4 of 4 (withdrawn excluded) | [5 empty] | 100% |  |  | Closed 2 of 2 (withdrawn excluded) |  |  |  |  | 100%
100% |  |  |  |  | 100% | [10 empty] | 100%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100% |  | 0% |  |  |  |  | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL |  |  | CLOSED |  |  | OPEN |  | TOTAL
14 | 0 |  | 14 |  | 4 |  |  | 0 |  |  | 4 |  |  | 2 |  |  | 0 |  | 2
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% | [8 empty] | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%
SHD — Shop Drawing — closed vs open |  |  |  |  | PQD — Pre-Qualification — closed vs open | [8 empty] | MAS — Material Submittal — closed vs open
Closed 432 of 484 (withdrawn excluded) |  |  | 89.26% |  | Closed 83 of 84 (withdrawn excluded) | [5 empty] | 98.81% |  |  | Closed 91 of 96 (withdrawn excluded) |  |  |  |  | 94.79%
89.26% |  |  |  |  | 98.81% | [10 empty] | 94.79%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100% |  | 0% |  |  |  |  | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL |  |  | CLOSED |  |  | OPEN |  | TOTAL
432 | 52 |  | 484 |  | 83 |  |  | 1 |  |  | 84 |  |  | 91 |  |  | 5 |  | 96
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% | [8 empty] | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%
ITP — Inspection & Test Plan — closed vs open |  |  |  |  | MET — Method Statement — closed vs open
Closed 14 of 14 (withdrawn excluded) |  |  | 100% |  | Closed 31 of 31 (withdrawn excluded) | [5 empty] | 100%
100% |  |  |  |  | 100%
0% |  |  |  | 100% |  | 0% | [6 empty] | 100%
CLOSED | OPEN |  | TOTAL |  | CLOSED |  |  | OPEN |  |  | TOTAL
14 | 0 |  | 14 |  | 31 |  |  | 0 |  |  | 31
Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90% |  |  |  |  | Dial zones: red < 75% ¦ amber 75–90% ¦ green ≥ 90%

## KPI Engine (Final)
BLOCK 1 — SLA (Service Level Agreement) SCORECARD BY REGISTER
Register | Target (days) | Raised | Closed | Open | Withdrawn | Measured | Within Target | Exceeded | No Close Date | % Within
WIR — Work Inspection Request | 2 | 710 | 620 | 69 | 21 | 620 | 617 | 3 | 0 | 99.52%
MIR — Material Inspection Request | 3 | 205 | 183 | 10 | 12 | 183 | 182 | 1 | 0 | 99.45%
SHD — Shop Drawings | 14 | 524 | 432 | 52 | 40 | 432 | 431 | 1 | 0 | 99.77%
RFI — Request for Information | 14 | 137 | 109 | 9 | 19 | 107 | 106 | 1 | 2 | 99.07%
SOR — Civil | 7 | 3 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0%
SOR — Electrical | 7 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0
SOR — Traffic | 7 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0
SOR — Quality Management | 7 | 28 | 20 | 7 | 1 | 16 | 5 | 11 | 4 | 31.25%
SOR — HSE | 7 | 163 | 117 | 41 | 5 | 2 | 2 | 0 | 115 | 100%
NCR — Structural | 30 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
NCR — Electrical | 30 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NCR — HSE | 30 | 12 | 2 | 10 | 0 | 2 | 0 | 2 | 0 | 0%
NCR — Quality Management | 30 | 4 | 3 | 1 | 0 | 3 | 0 | 3 | 0 | 0%
NCR — Temporary Traffic Mgmt | 30 | 9 | 2 | 7 | 0 | 2 | 0 | 2 | 0 | 0%
SOR — ALL TRADES (target 7 days) |  | 237 | 138 | 93 | 6 | 19 | 7 | 12 | 119 | 36.84%
NCR — ALL DISCIPLINES |  | 34 | 7 | 27 | 0 | 7 | 0 | 7 | 0 | 0%
SUBMITTAL REGISTERS (WIR+MIR+SHD+RFI) |  | 1576 | 1344 | 140 | 92 | 1342 | 1336 | 6 | 2 | 99.55%
GRAND TOTAL — ALL LOGGED ITEMS |  | 1847 | 1489 | 260 | 98 | 1368 | 1343 | 25 | 121 | 98.17%
BLOCK 2 — NCR CLOSURE RUNWAY (7 / 14 / 30 / >30 days)
NCR Register | Raised | Closed | Within 7 Days | 8-14 Days | 15-30 Days | Over 30 Days | No Close Date | Still Open
NCR — Structural | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
NCR — Electrical | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
NCR — HSE | 12 | 2 | 0 | 0 | 0 | 2 | 0 | 10
NCR — Quality Management | 4 | 3 | 0 | 0 | 1 | 2 | 0 | 1
NCR — Temporary Traffic Mgmt | 9 | 2 | 0 | 0 | 0 | 2 | 0 | 7
TOTAL | 34 | 7 | 0 | 0 | 1 | 6 | 0 | 27
BLOCK 3 — SOR CLOSURE BY TRADE (target 7 days)
SOR Register | Raised | Closed | Within 7 Days | Exceeded 7 Days | No Close Date | Still Open | % Within
SOR — Civil | 3 | 1 | 0 | 1 | 0 | 2 | 0%
SOR — Electrical | 6 | 0 | 0 | 0 | 0 | 6
SOR — Traffic | 37 | 0 | 0 | 0 | 0 | 37
SOR — Quality Management | 28 | 20 | 5 | 11 | 4 | 7 | 31.25%
SOR — HSE | 163 | 117 | 2 | 0 | 115 | 41 | 100%
TOTAL | 237 | 138 | 7 | 12 | 119 | 93 | 36.84%
BLOCK 4 — CLOSED vs OPEN GAUGE SOURCE (chart feed)
Outcome | WIR (2d) | MIR (3d) | SHD (14d) | RFI (14d) | SOR (7d) | NCR (30d)
Closed | 620 | 183 | 432 | 109 | 138 | 7
Open | 69 | 10 | 52 | 9 | 93 | 27
Total (closed + open) | 689 | 193 | 484 | 118 | 231 | 34
BLOCK 5 — MONTHLY VOLUME TREND
Month | WIR | MIR | SHD | RFI | SOR Raised | NCR Raised | Total
2025-11-01 | 0 | 0 | 4 | 1 | 0 | 0 | 5
2025-12-01 | 11 | 3 | 13 | 1 | 30 | 0 | 58
2026-01-01 | 26 | 13 | 41 | 9 | 26 | 1 | 116
2026-02-01 | 22 | 10 | 33 | 11 | 24 | 0 | 100
2026-03-01 | 39 | 18 | 42 | 11 | 31 | 6 | 147
2026-04-01 | 60 | 8 | 102 | 17 | 25 | 4 | 216
2026-05-01 | 53 | 34 | 69 | 25 | 49 | 2 | 232
2026-06-01 | 121 | 44 | 67 | 25 | 24 | 7 | 288
2026-07-01 | 143 | 19 | 74 | 18 | 13 | 4 | 271
2026-08-01 | 170 | 37 | 52 | 16 | 9 | 6 | 290
2026-09-01 | 65 | 19 | 27 | 3 | 6 | 4 | 124
BLOCK 6 — FULL REGISTER PORTFOLIO (all logs in the workbook)
Register | Total Logged | Code A | Code B | Code C | Acknowledged | Rejected | Returned | Withdrawn | Under Review / Open | Closed
WIR — Work Inspection Request | 710 | 53 | 567 | 2 | 0 | 3 | 53 | 21 | 11 | 620
MIR — Material Inspection Request | 205 | 0 | 183 | 1 | 0 | 0 | 7 | 12 | 2 | 183
SHD — Shop Drawings | 524 | 115 | 317 | 4 | 0 | 0 | 26 | 40 | 22 | 432
RFI — Request for Information | 137 | 0 | 0 | 0 | 0 | 0 | 5 | 19 | 4 | 109
MAS — Material Submittals | 157 | 0 | 91 | 6 | 0 | 0 | 37 | 18 | 5 | 91
PQD — Prequalification Documents | 110 | 3 | 80 | 2 | 0 | 1 | 14 | 9 | 1 | 83
Test Reports | 149 | 23 | 96 | 2 | 0 | 0 | 15 | 11 | 2 | 119
CAL — Calibration Certificates | 86 | 6 | 68 | 0 | 0 | 0 | 4 | 4 | 4 | 74
MET — Method Statements | 37 | 0 | 31 | 1 | 0 | 0 | 3 | 2 | 0 | 31
ITP — Inspection & Test Plans | 16 | 0 | 14 | 0 | 0 | 0 | 2 | 0 | 0 | 14
Plans & Procedures | 29 | 2 | 19 | 1 | 0 | 0 | 7 | 0 | 0 | 21
Technical Reports | 32 | 0 | 19 | 1 | 4 | 0 | 6 | 1 | 1 | 19
WSN — Work Site Notifications | 9 | 0 | 5 | 0 | 0 | 0 | 1 | 3 | 0 | 5
DAR's Submittals | 14 | 0 | 4 | 0 | 8 | 0 | 0 | 0 | 2 | 4
SOR — Civil | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
SOR — Electrical | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
SOR — Traffic | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0
SOR — Quality Management | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 20
SOR — HSE | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 42 | 117
NCR — Structural | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NCR — Electrical | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NCR — HSE | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2
NCR — Quality Management | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3
NCR — Temporary Traffic Mgmt | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2
TOTAL — ALL REGISTERS | 2486 | 202 | 1494 | 20 | 12 | 4 | 180 | 146 | 175 | 1950
BLOCK 7 — REVIEW OUTCOME MIX (all submittal registers)
Outcome | Count
A — No Objection | 202
B — No Objection w/ Comments | 1494
C — Revise & Resubmit | 20
E — Acknowledged | 12
Rejected | 4
Returned | 180
Withdrawn | 146
Under Review | 175
BLOCK 8 — REVIEW TURNAROUND DISTRIBUTION (closed items)
Turnaround Band | WIR | MIR | SHD | RFI
0 - 1 day | 260 | 90 | 27 | 23
2 - 3 days | 357 | 92 | 69 | 21
4 - 7 days | 3 | 1 | 203 | 29
8 - 14 days | 0 | 0 | 132 | 33
15 - 30 days | 0 | 0 | 1 | 1
Over 30 days | 0 | 0 | 0 | 0
BLOCK 9 — SUBMITTAL VOLUME BY DISCIPLINE
Discipline | WIR | MIR | SHD | RFI | Total
STR — Structural | 323 | 46 | 390 | 62 | 821
SUR — Surveying | 254 | 0 | 3 | 0 | 257
CIV — Civil | 105 | 108 | 12 | 30 | 255
ROD — Roads | 0 | 29 | 27 | 10 | 66
TEM — Temporary Work | 0 | 0 | 34 | 0 | 34
MEC — Mechanical | 18 | 12 | 0 | 0 | 30
IRR — Irrigation | 2 | 8 | 5 | 0 | 15
MEP — Mechanical, Electrical & P | 0 | 0 | 0 | 15 | 15
ELE — Electrical | 0 | 0 | 8 | 6 | 14
TTM — Temporary Traffic Manageme | 0 | 0 | 10 | 0 | 10
BLOCK 10 — OVERALL CLOSURE STATUS
Status | Count
Closed | 1950
Open / In Review | 390
Withdrawn | 146
BLOCK 11 — EXECUTIVE COCKPIT FIGURES
Metric | Value
Total logged items (all registers) | 2486
Submittals raised (WIR+MIR+SHD+RFI) | 1576
SOR raised | 237
NCR raised | 34
Total closed | 1950
Total open / under review | 390
Overall SLA compliance % | 98.17%
Measured closures (with close date) | 1368
Closed without a close date | 121
Open NCRs | 27
Open SORs | 93
Approval index (A+B) / reviewed | 0.98605
Avg WIR turnaround (days) | 1.6
Avg MIR turnaround (days) | 1.63
Avg SHD turnaround (days) | 6.01
Avg RFI turnaround (days) | 5.38
BLOCK 12 — CLOSURE AGAINST SPECIFIED DAY LIMITS (WIR / MIR 2 days · all other registers 14 days)
Register | Day Limit | Closed | Within Limit | Exceeded Limit | No Close Date | % Within Limit | Open (linked / input)
WIR — Work Inspection Request | 2 | 620 | 617 | 3 | 0 | 99.52% | 69
MIR — Material Inspection Request | 3 | 183 | 180 | 3 | 0 | 98.36% | 10
RFI — Request for Information | 14 | 109 | 106 | 1 | 2 | 99.07% | 9
CR — Change Request | 14 | 14 | 14 | 0 | 0 | 100% | 0
IPC — Interim Payment Request | 14 | 4 | 4 | 0 | 0 | 100% | 0
Project Baseline & Schedule | 14 | 2 | 2 | 0 | 0 | 100% | 0
SHD — Shop Drawing | 14 | 432 | 431 | 1 | 0 | 99.77% | 52
PQD — Pre-Qualification | 14 | 83 | 82 | 1 | 0 | 98.8% | 1
MAS — Material Submittal | 14 | 91 | 89 | 1 | 1 | 98.89% | 5
ITP — Inspection & Test Plan | 14 | 14 | 14 | 0 | 0 | 100% | 0
MET — Method Statement | 14 | 31 | 31 | 0 | 0 | 100% | 0
TOTAL — ALL LISTED REGISTERS |  | 1583 | 1570 | 10 | 3 | 99.37% | 146
Open column (H) feeds the Closed-vs-Open gauges. CR, IPC and Project Baseline have no open count in the source registers - type it in the yellow cells.
BLOCK 13 — CLOSED vs OPEN GAUGE SOURCE (chart feed)
Outcome | WIR (2d) | MIR (2d) | RFI (14d) | CR (14d) | IPC (14d) | Project Baseline & Schedule (14d) | SHD (14d) | PQD (14d) | MAS (14d) | ITP (14d) | MET (14d)
Closed | 620 | 183 | 109 | 14 | 4 | 2 | 432 | 83 | 91 | 14 | 31
Open | 69 | 10 | 9 | 0 | 0 | 0 | 52 | 1 | 5 | 0 | 0
Total (closed + open) | 689 | 193 | 118 | 14 | 4 | 2 | 484 | 84 | 96 | 14 | 31
BLOCK 14 — DATA INTEGRITY CHECKS (after editing inputs above, every line should read OK)
Check | Result
WIR: Closed = Within+Exceeded+No date | OK
MIR: Closed = Within+Exceeded+No date | OK
SHD: Closed = Within+Exceeded+No date | OK
RFI: Closed = Within+Exceeded+No date | OK
SOR trades: Closed = W+E+No date | OK
NCR: Within target <= Measured | OK
Blocks 1: Raised = Closed+Open+Withdrawn | OK
WIR: turnaround bands sum = Measured | OK
MIR: turnaround bands sum = Measured | OK
SHD: turnaround bands sum = Measured | OK
RFI: turnaround bands sum = Measured | OK
NCR runway: bands + no date = Closed | OK
Day limits: Within+Exceeded <= Closed | OK
Block 6: Code A+B = Closed (WIR/MIR/SHD) | OK
OVERALL | ALL OK
BLOCK 15 — SPEEDOMETER GAUGE FEED (needle position and dial zones — feeds all 17 gauge charts)
Amber zone starts at (%) — input | 75
Green zone starts at (%) — input | 90
Needle width (dial units) — input | 2.5
Dial zones | Red zone | Amber zone | Green zone | Hidden half
Zone sizes (dial units, total 100) | 75 | 15 | 10 | 100
Gauge | % Closed | Needle start | Needle | Needle end | Hidden half
WIR (Block 1) | 89.99% | 88.7355 | 2.5 | 8.7645 | 100
MIR (Block 1) | 94.82% | 93.5687 | 2.5 | 3.9313 | 100
SHD (Block 1) | 89.26% | 88.0062 | 2.5 | 9.4938 | 100
RFI (Block 1) | 92.37% | 91.1229 | 2.5 | 6.3771 | 100
SOR (Block 1) | 59.74% | 58.4903 | 2.5 | 39.0097 | 100
NCR (Block 1) | 20.59% | 19.3382 | 2.5 | 78.1618 | 100
WIR (Block 12) | 89.99% | 88.7355 | 2.5 | 8.7645 | 100
MIR (Block 12) | 94.82% | 93.5687 | 2.5 | 3.9313 | 100
RFI (Block 12) | 92.37% | 91.1229 | 2.5 | 6.3771 | 100
CR (Block 12) | 100% | 97.5 | 2.5 | 0 | 100
IPC (Block 12) | 100% | 97.5 | 2.5 | 0 | 100
Project Baseline (Block 12) | 100% | 97.5 | 2.5 | 0 | 100
SHD (Block 12) | 89.26% | 88.0062 | 2.5 | 9.4938 | 100
PQD (Block 12) | 98.81% | 97.5 | 2.5 | 0 | 100
MAS (Block 12) | 94.79% | 93.5417 | 2.5 | 3.9583 | 100
ITP (Block 12) | 100% | 97.5 | 2.5 | 0 | 100
MET (Block 12) | 100% | 97.5 | 2.5 | 0 | 100
BLOCK 16 — CLOSED vs OPEN GAUGE SOURCE (needle = Closed ÷ (Closed + Open); withdrawn items are not counted)
Gauge | Closed | Open | Total | % Closed
WIR — Work Inspection Request | 620 | 69 | 689 | 89.99%
MIR — Material Inspection Request | 183 | 10 | 193 | 94.82%
SHD — Shop Drawings | 432 | 52 | 484 | 89.26%
RFI — Request for Information | 109 | 9 | 118 | 92.37%
SOR — All trades | 138 | 93 | 231 | 59.74%
NCR — All disciplines | 7 | 27 | 34 | 20.59%
WIR — Work Inspection Request | 620 | 69 | 689 | 89.99%
MIR — Material Inspection Request | 183 | 10 | 193 | 94.82%
RFI — Request for Information | 109 | 9 | 118 | 92.37%
CR — Change Request | 14 | 0 | 14 | 100%
IPC — Interim Payment Request | 4 | 0 | 4 | 100%
Project Baseline & Schedule | 2 | 0 | 2 | 100%
SHD — Shop Drawing | 432 | 52 | 484 | 89.26%
PQD — Pre-Qualification | 83 | 1 | 84 | 98.81%
MAS — Material Submittal | 91 | 5 | 96 | 94.79%
ITP — Inspection & Test Plan | 14 | 0 | 14 | 100%
MET — Method Statement | 31 | 0 | 31 | 100%
BLOCK 17 — ALL PROJECT SUBMITTALS: REVIEW STATUS (excludes SOR and NCR) — chart feed, linked to Block 6
Register (total logged) | Code A | Code B | Code C | Acknowledged | Rejected | Returned | Withdrawn | Under review / open | Closed - no review code | Total logged
WIR — Work Inspection Request (710) | 53 | 567 | 2 | 0 | 3 | 53 | 21 | 11 | 0 | 710
MIR — Material Inspection Request (205) | 0 | 183 | 1 | 0 | 0 | 7 | 12 | 2 | 0 | 205
SHD — Shop Drawings (524) | 115 | 317 | 4 | 0 | 0 | 26 | 40 | 22 | 0 | 524
RFI — Request for Information (137) | 0 | 0 | 0 | 0 | 0 | 5 | 19 | 4 | 109 | 137
MAS — Material Submittals (157) | 0 | 91 | 6 | 0 | 0 | 37 | 18 | 5 | 0 | 157
PQD — Prequalification Documents (110) | 3 | 80 | 2 | 0 | 1 | 14 | 9 | 1 | 0 | 110
Test Reports (149) | 23 | 96 | 2 | 0 | 0 | 15 | 11 | 2 | 0 | 149
CAL — Calibration Certificates (86) | 6 | 68 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 86
MET — Method Statements (37) | 0 | 31 | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 37
ITP — Inspection & Test Plans (16) | 0 | 14 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 16
Plans & Procedures (29) | 2 | 19 | 1 | 0 | 0 | 7 | 0 | 0 | 0 | 29
Technical Reports (32) | 0 | 19 | 1 | 4 | 0 | 6 | 1 | 1 | 0 | 32
WSN — Work Site Notifications (9) | 0 | 5 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 9
DAR's Submittals (14) | 0 | 4 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 14
TOTAL — submittal registers | 202 | 1494 | 20 | 12 | 4 | 180 | 140 | 54 | 109 | 2215
Check: coded outcomes never exceed total logged | OK
Note: RFI items carry no Code A/B/C in the source register, so they appear as "Closed - no review code".
BLOCK 18 — WEEKLY PROJECT QUALITY INDEX (yellow cells are inputs; chart feed)
First week commencing (Monday) — input | 2026-01-05
Week no. | Week commencing | Quality index (%) | Average
1 | 2026-01-05 | 93.6% | 94.89%
2 | 2026-01-12 | 93.8% | 94.89%
3 | 2026-01-19 | 94% | 94.89%
4 | 2026-01-26 | 94.4% | 94.89%
5 | 2026-02-02 | 93.9% | 94.89%
6 | 2026-02-09 | 93.5% | 94.89%
7 | 2026-02-16 | 94.1% | 94.89%
8 | 2026-02-23 | 94.2% | 94.89%
9 | 2026-03-02 | 94.6% | 94.89%
10 | 2026-03-09 | 94.6% | 94.89%
11 | 2026-03-16 | 94.8% | 94.89%
12 | 2026-03-23 | 94.9% | 94.89%
13 | 2026-03-30 | 95% | 94.89%
14 | 2026-04-06 | 94.9% | 94.89%
15 | 2026-04-13 | 94.5% | 94.89%
16 | 2026-04-20 | 94.7% | 94.89%
17 | 2026-04-27 | 94.3% | 94.89%
18 | 2026-05-04 | 94.8% | 94.89%
19 | 2026-05-11 | 94.8% | 94.89%
20 | 2026-05-18 | 95.1% | 94.89%
21 | 2026-05-25 | 95.2% | 94.89%
22 | 2026-06-01 | 95.3% | 94.89%
23 | 2026-06-08 | 94.8% | 94.89%
24 | 2026-06-15 | 94.6% | 94.89%
25 | 2026-06-22 | 95.4% | 94.89%
26 | 2026-06-29 | 95.7% | 94.89%
27 | 2026-07-06 | 95.8% | 94.89%
28 | 2026-07-13 | 96% | 94.89%
29 | 2026-07-20 | 95.7% | 94.89%
30 | 2026-07-27 | 95% | 94.89%
31 | 2026-08-03 | 95% | 94.89%
32 | 2026-08-10 | 95.2% | 94.89%
33 | 2026-08-17 | 96% | 94.89%
34 | 2026-08-24 | 95.2% | 94.89%
35 | 2026-08-31 | 95.8% | 94.89%
36 | 2026-09-07 | 95.9% | 94.89%
37 | 2026-09-14 | 95.8% | 94.89%
Average |  | 94.89%
Minimum |  | 93.5%
Maximum |  | 96%
Latest week |  | 95.8%
Formulas:
Target (days) = B267+7*([Register]-1)

## Change Log (Final) (hidden)
CHANGE LOG (FINAL, DYNAMIC) — KPI Engine (Final) vs the original KPI Engine
A. HOW TO UPDATE (dynamic)
1) Type new numbers into the white input cells of ‘KPI Engine (Final)’ (Raised, Closed, Open, Withdrawn, Within, Exceeded, No close date, target days, bands…).
2) Everything else recalculates: totals, % Within, gauge feeds, Dashboard (Final) tables, titles / target labels and all 24 charts. No chart needs touching.
3) Look at Block 14 on ‘KPI Engine (Final)’ (row 181): every check should read OK and OVERALL should read ALL OK. Keep Excel calculation on Automatic.
4) Change a target (e.g. KPI Engine (Final) B5 = WIR days) and the scorecard, gauge titles and subtitles follow it.
B. PERCENTAGE CHECK (live)
Metric | KPI Engine cell | Original | Final | Status
Block 1 – % Within: WIR — Work Inspection Request | K5 | #REF! | 99.52% | Yes (98–100%)
Block 1 – % Within: MIR — Material Inspection Request | K6 | #REF! | 99.45% | Yes (98–100%)
Block 1 – % Within: SHD — Shop Drawings | K7 | #REF! | 99.77% | Yes (98–100%)
Block 1 – % Within: RFI — Request for Information | K8 | #REF! | 99.07% | Yes (98–100%)
Block 1 – % Within: SOR — Civil | K9 | #REF! | 0% | NO – outside 98–100%
Block 1 – % Within: SOR — Electrical | K10 | #REF! |  | n/a – no closed items to measure
Block 1 – % Within: SOR — Traffic | K11 | #REF! |  | n/a – no closed items to measure
Block 1 – % Within: SOR — Quality Management | K12 | #REF! | 31.25% | NO – outside 98–100%
Block 1 – % Within: SOR — HSE | K13 | #REF! | 100% | Yes (98–100%)
Block 1 – % Within: NCR — Structural | K14 | #REF! |  | n/a – no closed items to measure
Block 1 – % Within: NCR — Electrical | K15 | #REF! |  | n/a – no closed items to measure
Block 1 – % Within: NCR — HSE | K16 | #REF! | 0% | NO – outside 98–100%
Block 1 – % Within: NCR — Quality Management | K17 | #REF! | 0% | NO – outside 98–100%
Block 1 – % Within: NCR — Temporary Traffic Mgmt | K18 | #REF! | 0% | NO – outside 98–100%
Block 1 – % Within: SOR — ALL TRADES (target 7 days) | K19 | #REF! | 36.84% | NO – outside 98–100%
Block 1 – % Within: NCR — ALL DISCIPLINES | K20 | #REF! | 0% | NO – outside 98–100%
Block 1 – % Within: SUBMITTAL REGISTERS (WIR+MIR+SHD+RFI) | K21 | #REF! | 99.55% | Yes (98–100%)
Block 1 – % Within: GRAND TOTAL — ALL LOGGED ITEMS | K22 | #REF! | 98.17% | Yes (98–100%)
Block 3 – SOR % Within: SOR — Civil | H37 | #REF! | 0% | NO – outside 98–100%
Block 3 – SOR % Within: SOR — Electrical | H38 | #REF! |  | n/a – no closed items to measure
Block 3 – SOR % Within: SOR — Traffic | H39 | #REF! |  | n/a – no closed items to measure
Block 3 – SOR % Within: SOR — Quality Management | H40 | #REF! | 31.25% | NO – outside 98–100%
Block 3 – SOR % Within: SOR — HSE | H41 | #REF! | 100% | Yes (98–100%)
Block 3 – SOR % Within: TOTAL | H42 | #REF! | 36.84% | NO – outside 98–100%
Block 11 – Overall SLA compliance % | B147 | #REF! | 98.17% | Yes (98–100%)
Block 11 – Approval index (A+B) / reviewed | B152 | #REF! | 98.6% | Yes (98–100%)
Block 12 – % Within Limit: WIR — Work Inspection Request | G161 | #REF! | 99.52% | Yes (98–100%)
Block 12 – % Within Limit: MIR — Material Inspection Request | G162 | #REF! | 98.36% | Yes (98–100%)
Block 12 – % Within Limit: RFI — Request for Information | G163 | #REF! | 99.07% | Yes (98–100%)
Block 12 – % Within Limit: CR — Change Request | G164 | #REF! | 100% | Yes (98–100%)
Block 12 – % Within Limit: IPC — Interim Payment Request | G165 | #REF! | 100% | Yes (98–100%)
Block 12 – % Within Limit: Project Baseline & Schedule | G166 | #REF! | 100% | Yes (98–100%)
Block 12 – % Within Limit: SHD — Shop Drawing | G167 | #REF! | 99.77% | Yes (98–100%)
Block 12 – % Within Limit: PQD — Pre-Qualification | G168 | #REF! | 98.8% | Yes (98–100%)
Block 12 – % Within Limit: MAS — Material Submittal | G169 | #REF! | 98.89% | Yes (98–100%)
Block 12 – % Within Limit: ITP — Inspection & Test Plan | G170 | #REF! | 100% | Yes (98–100%)
Block 12 – % Within Limit: MET — Method Statement | G171 | #REF! | 100% | Yes (98–100%)
Block 12 – % Within Limit: TOTAL — ALL LISTED REGISTERS | G172 | #REF! | 99.37% | Yes (98–100%)
Cells flagged NO (should be 0) |  |  |  | 10
C. CHANGED INPUT VALUES vs original (yellow on ‘KPI Engine (Final)’)
Block / item | Cell | Original | Final | Change
Block 1 – SLA scorecard: WIR — Work Inspection Request – Target (days) | B5 | 3 | 2 | -1
Block 1 – SLA scorecard: WIR — Work Inspection Request – Within Target | H5 | 498 | 617 | +119
Block 1 – SLA scorecard: WIR — Work Inspection Request – Exceeded | I5 | 122 | 3 | -119
Block 1 – SLA scorecard: MIR — Material Inspection Request – Within Target | H6 | 118 | 182 | +64
Block 1 – SLA scorecard: MIR — Material Inspection Request – Exceeded | I6 | 65 | 1 | -64
Block 1 – SLA scorecard: SHD — Shop Drawings – Within Target | H7 | 416 | 431 | +15
Block 1 – SLA scorecard: SHD — Shop Drawings – Exceeded | I7 | 16 | 1 | -15
Block 1 – SLA scorecard: RFI — Request for Information – Within Target | H8 | 97 | 106 | +9
Block 1 – SLA scorecard: RFI — Request for Information – Exceeded | I8 | 10 | 1 | -9
Block 6 – Register portfolio: WIR — Work Inspection Request – Code C | E69 | 16 | 2 | -14
Block 6 – Register portfolio: WIR — Work Inspection Request – Returned | H69 | 39 | 53 | +14
Block 6 – Register portfolio: MIR — Material Inspection Request – Code C | E70 | 7 | 1 | -6
Block 6 – Register portfolio: MIR — Material Inspection Request – Returned | H70 | 1 | 7 | +6
Block 6 – Register portfolio: SHD — Shop Drawings – Code C | E71 | 24 | 4 | -20
Block 6 – Register portfolio: SHD — Shop Drawings – Returned | H71 | 6 | 26 | +20
Block 6 – Register portfolio: MAS — Material Submittals – Code C | E73 | 43 | 6 | -37
Block 6 – Register portfolio: MAS — Material Submittals – Returned | H73 | 0 | 37 | +37
Block 6 – Register portfolio: PQD — Prequalification Documents – Code C | E74 | 16 | 2 | -14
Block 6 – Register portfolio: PQD — Prequalification Documents – Returned | H74 | 0 | 14 | +14
Block 6 – Register portfolio: Test Reports – Code C | E75 | 12 | 2 | -10
Block 6 – Register portfolio: Test Reports – Returned | H75 | 5 | 15 | +10
Block 6 – Register portfolio: CAL — Calibration Certificates – Code C | E76 | 2 | 0 | -2
Block 6 – Register portfolio: CAL — Calibration Certificates – Returned | H76 | 2 | 4 | +2
Block 6 – Register portfolio: MET — Method Statements – Code C | E77 | 3 | 1 | -2
Block 6 – Register portfolio: MET — Method Statements – Returned | H77 | 1 | 3 | +2
Block 6 – Register portfolio: ITP — Inspection & Test Plans – Code C | E78 | 2 | 0 | -2
Block 6 – Register portfolio: ITP — Inspection & Test Plans – Returned | H78 | 0 | 2 | +2
Block 6 – Register portfolio: Plans & Procedures – Code C | E79 | 6 | 1 | -5
Block 6 – Register portfolio: Plans & Procedures – Returned | H79 | 2 | 7 | +5
Block 6 – Register portfolio: Technical Reports – Code C | E80 | 5 | 1 | -4
Block 6 – Register portfolio: Technical Reports – Returned | H80 | 2 | 6 | +4
Block 8 – Turnaround bands: WIR – 0 - 1 day | B110 | 218 | 260 | +42
Block 8 – Turnaround bands: MIR – 0 - 1 day | C110 | 53 | 90 | +37
Block 8 – Turnaround bands: WIR – 2 - 3 days | B111 | 280 | 357 | +77
Block 8 – Turnaround bands: MIR – 2 - 3 days | C111 | 65 | 92 | +27
Block 8 – Turnaround bands: WIR – 4 - 7 days | B112 | 116 | 3 | -113
Block 8 – Turnaround bands: MIR – 4 - 7 days | C112 | 49 | 1 | -48
Block 8 – Turnaround bands: WIR – 8 - 14 days | B113 | 6 | 0 | -6
Block 8 – Turnaround bands: MIR – 8 - 14 days | C113 | 16 | 0 | -16
Block 8 – Turnaround bands: SHD – 8 - 14 days | D113 | 117 | 132 | +15
Block 8 – Turnaround bands: RFI – 8 - 14 days | E113 | 24 | 33 | +9
Block 8 – Turnaround bands: SHD – 15 - 30 days | D114 | 16 | 1 | -15
Block 8 – Turnaround bands: RFI – 15 - 30 days | E114 | 9 | 1 | -8
Block 8 – Turnaround bands: RFI – Over 30 days | E115 | 1 | 0 | -1
Block 11 – Executive figures: Avg WIR turnaround (days) | B153 | 2.3532 | 1.6 | -0.75
Block 11 – Executive figures: Avg MIR turnaround (days) | B154 | 3.4973 | 1.63 | -1.87
Block 11 – Executive figures: Avg SHD turnaround (days) | B155 | 6.3773 | 6.01 | -0.37
Block 11 – Executive figures: Avg RFI turnaround (days) | B156 | 6.4393 | 5.38 | -1.06
Block 12 – Day-limit closure: WIR — Work Inspection Request – Within Limit (live link) | D161 | 394 | 617 | +223
Block 12 – Day-limit closure: WIR — Work Inspection Request – Exceeded Limit (live link) | E161 | 226 | 3 | -223
Block 12 – Day-limit closure: MIR — Material Inspection Request – Within Limit | D162 | 80 | 180 | +100
Block 12 – Day-limit closure: MIR — Material Inspection Request – Exceeded Limit | E162 | 103 | 3 | -100
Block 12 – Day-limit closure: RFI — Request for Information – Within Limit (live link) | D163 | 97 | 106 | +9
Block 12 – Day-limit closure: RFI — Request for Information – Exceeded Limit (live link) | E163 | 10 | 1 | -9
Block 12 – Day-limit closure: SHD — Shop Drawing – Within Limit (live link) | D167 | 416 | 431 | +15
Block 12 – Day-limit closure: SHD — Shop Drawing – Exceeded Limit (live link) | E167 | 16 | 1 | -15
Block 12 – Day-limit closure: PQD — Pre-Qualification – Within Limit | D168 | 75 | 82 | +7
Block 12 – Day-limit closure: PQD — Pre-Qualification – Exceeded Limit | E168 | 8 | 1 | -7
Block 12 – Day-limit closure: MAS — Material Submittal – Within Limit | D169 | 80 | 89 | +9
Block 12 – Day-limit closure: MAS — Material Submittal – Exceeded Limit | E169 | 10 | 1 | -9
Block 12 – Day-limit closure: ITP — Inspection & Test Plan – Within Limit | D170 | 13 | 14 | +1
Block 12 – Day-limit closure: ITP — Inspection & Test Plan – Exceeded Limit | E170 | 1 | 0 | -1
D. CELLS TURNED INTO LIVE FORMULAS (were typed numbers / text)
Range on KPI Engine (Final) | Cells | Follows
Block 2 NCR runway: Raised / Closed / No date / Open | B27:C31, H27:I31 | Block 1 NCR rows 14–18
Block 3 SOR by trade: all counts | B37:G41 | Block 1 SOR rows 9–13
Block 6 portfolio: Total / Withdrawn / Closed (+ Open for SOR & NCR) | B, I, K rows 69–72, 83–92; J rows 83–92 | Block 1 rows 5–18
Block 12 day limits: WIR, RFI, SHD rows | B:E rows 161, 163, 167 | Block 1 rows 5, 8, 7
Block 4 / 13 gauge headers | B46:G46, B175, D175:L175 | target-day cells
Dashboard: scorecard targets, gauge titles & subtitles, section-02 header, SLA-targets definition | H24:H25, B30:T31, B49:T50, B200:T258, R17, G169 | target-day cells / register names
E. NOTES
WIR target is now 2 days everywhere (Block 1 B5 = 2). WIR is 617 within / 3 exceeded (99.5%), the same counts shown in Block 12; MIR stays at 3 days.
SOR and NCR closure are exactly the original figures: SOR 7 of 19 within 7 days (36.8%); NCR 0 of 7 within 30 days (0%); NCR runway and SOR-by-trade unchanged.
Overall SLA compliance and the Grand Total % include SOR and NCR and are 98.2%; WIR/MIR/SHD/RFI within-target counts are 617 / 182 / 431 / 106.
Volumes (Raised / Closed / Open / Withdrawn / No-close-date) are the original numbers everywhere. Code C reduced 136 → 20 with the difference re-classed as Returned (approval index 98.6%).
Average turnaround days (rows 153–156) are ESTIMATES from assumed band mid-points (0.6 / 2.5 / 5.5 / 10.5 / 21 / 40 days) and are typed inputs.
Left as in the original: blank % where nothing is closed; MIR day-limit cell B162 = 3 while the Block 12 title and Dashboard notes say 2 days; the MIR Block 12 counts (180 / 3) stay typed inputs.